MASTER RESEARCH CHARTER

Version 2.0  —  Traceability-Core Architecture

Data-informed Digital Twin Framework for Condition Monitoring

and Inspection–Maintenance Support of Coastal Industrial Steel Buildings

Field: Construction Management / Asset Management

Status: Source of truth. Supersedes v1.1 (LIMITED-FEM). Realigns the thesis onto a Construction-Management traceability-and-accountability core.

Approved basis: Council review sessions 17–19/07/2026; supervisor Verdict B (17/07/2026); LIMITED-FEM architecture retained.

Date: 2026-07-19

Contents

1.  What changed from v1.1 (and why)	3

2.  Central axis of the thesis	3

Core evidence chain (locked)	4

Core identifier chain (locked)	4

3.  Research questions (re-framed through the management lens)	4

4.  Chapter ↔ Question ↔ Paper mapping	4

5.  Paper portfolio and the 3-year / 2×Q3 plan	5

6.  Making the QLXD core unmistakable (Paper 2 / C5)	6

7.  Work packages	6

8.  Validation ladder	6

9.  Evidence gates	7

10.  Allowed and prohibited claims	7

Allowed	7

Prohibited	7

11.  Role of the nominal FEM	8

12.  Execution roadmap (3 years)	8

Immediate blockers	8

Year 1	8

Year 2	8

Year 3	8

Discipline guardrail	8

13.  Post-PhD extensions (deferred, ordered by value-nearness)	9

14.  Terminology control	9

# 1.  What changed from v1.1 (and why)

v1.1 correctly demoted FEM to a nominal reference tool and named traceability as the thesis core. But the research questions were still written in ontology-engineering language (IFC GlobalId, SHACL, provenance, competency questions). A Construction-Management (QLXD) defence panel would recognise a strong information-modelling contribution — but ask the decisive question: “what management decision does this change, and who is accountable for it?”

v2 fixes this by re-framing, not by adding scope. Three elements are now embedded into the core so the QLXD contribution is unmistakable:

- CEI as a first-class attribute of the traceability chain — evidence is linked together with its own confidence, not linked bare.

- Justification & accountability as the end purpose — traceability serves a verifiable, auditable inspection decision; it is not a contribution in itself.

- “Limited field damage data” as the defining boundary condition — the thesis solves the inverse problem most SHM/DT literature avoids: how to manage inspection when evidence is sparse and uncertain.

| Element | v1.1 (Limited-FEM) | v2 (Traceability-Core) |
| --- | --- | --- |
| Framing of RQ2 | Organise/link sensor evidence to BIM & inspection records (information modelling) | Organise evidence + CEI into a verifiable chain so inspection decisions are justified & accountable under sparse data |
| CEI | Confidence indicator, mostly a Paper 1 by-product | First-class attribute of the identifier chain; backbone of Paper 2 |
| Decision logic (4-level) | Deferred to WP4 / optional Paper 4 | Minimal version pulled into Paper 2 as the application layer of the chain |
| Legal mapping | Background context | Explicit article-level mapping = the QLXD anchor |
| Paper 3 (field) | Load-bearing pillar | Bonus / stretch; not on the critical path |
| FEM | Nominal reference only | Unchanged — nominal, uncalibrated, reference-only |

# 2.  Central axis of the thesis

A data-informed Digital Twin framework organises condition evidence — together with its confidence (CEI) — into a verifiable traceability chain to BIM components and inspection records, so that inspection–maintenance decisions can be justified and their accountability traced, even under limited field damage data. A nominal FEM model serves only as a sensor-placement reference, never as a diagnostic source.

QLXD core = justification & accountability of an asset-management decision under sparse-evidence constraints. Not damage diagnosis. Not sensor engineering.

## Core evidence chain (locked)

Vibration data
  → condition / state-change evidence (+ CEI)
    → BIM-linked component
      → inspection record
        → justified, accountable inspection–maintenance action

## Core identifier chain (locked)

Sensor_ID → BIM_GUID → Condition_Evidence_ID (+CEI) → Inspection_Record_ID → Action_Status

CEI is now an explicit attribute of every Condition_Evidence_ID. FEM_Node_ID may exist only as optional metadata; it never appears as a required link.

# 3.  Research questions (re-framed through the management lens)

RQ1 — Evidence

Under a run-aware, leakage-controlled (LORO) protocol, to what confidence can vibration data from the 1:10 steel frame and different sensor configurations produce evidence distinguishing controlled connection states — and does sensor configuration dominate model-architecture choice?

RQ2 — Traceability & decision  (QLXD core)

How can condition evidence — carrying a confidence/evidence indicator (CEI) — be organised and linked to BIM components and inspection records as a verifiable traceability chain, so that an inspection decision can be justified and its accountability traced, even when field damage data are limited?

RQ3 — Field feasibility  (bonus / stretch)

To what extent can the framework be deployed at a real industrial steel building (Rapexco) to support the selection and recording of inspection actions under limited field damage data?

# 4.  Chapter ↔ Question ↔ Paper mapping

The load-bearing spine is C4 (Paper 1 / RQ1) and C5 (Paper 2 / RQ2). Both are workstation-only and can run in parallel now. C6 (Paper 3 / RQ3, Rapexco) is a bonus prepared only after Papers 1–2 are submitted. There is no FEM chapter.

| Chapter | Content | RQ | Paper | QLXD role |
| --- | --- | --- | --- | --- |
| C1 | Introduction; asset-management context of coastal steel buildings | — | — | Frames the management problem |
| C2 | Literature & gap = missing evidence→component→record→justified-action chain | — | — | Positions the gap as a management gap, not a technical one |
| C3 | Research framework; DT management-maturity self-definition; nominal-FEM subsection | — | — | Positive-contribution statement |
| C4 | Lab evidence; run-aware/LORO; sensor-configuration effect; CEI as confidence indicator | RQ1 | Paper 1 | Evidence base with quantified confidence |
| C5 | Traceability-to-decision framework: identifier chain + CEI; SCQ/VCQ/RCQ; invalid-data test; legal mapping; minimal 4-level logic | RQ2 | Paper 2 | QLXD CORE — identity pillar |
| C6 | Rapexco field feasibility: Sensor→BIM mapping, baseline, inspection scenarios | RQ3 | Paper 3 (bonus) | Feasibility evidence |
| C7 | (optional, may merge into C6) extended 4-level logic + expert review | RQ3 | Paper 4 (opt.) | — |
| C8 | Conclusions, contributions, post-PhD extensions | — | — | — |

# 5.  Paper portfolio and the 3-year / 2×Q3 plan

Minimum requirement: two Q3 papers in three years. Load-bearing pillars = Paper 1 (RQ1) + Paper 2 (RQ2). Neither depends on site access. Paper 3 (Rapexco) is a bonus with a real physical base but off the critical path.

| Paper | Working title | Core content | Target (verify rank before locking) |
| --- | --- | --- | --- |
| Paper 1 | Run-Aware Evaluation of Low-Cost Sensor Configurations for Vibration-Based Condition Classification of a Scaled Bolted Steel Frame | Dataset integrity, run registry, run-aware/LORO, sensor-configuration effect, CEI as confidence indicator | Sensors (primary) |
| Paper 2 | A Verifiable Traceability-to-Decision Framework Linking Condition Evidence and Confidence to BIM Objects and Inspection Records for Industrial Steel Buildings | Identifier chain + CEI, pre-registered SCQ/VCQ/RCQ, invalid-data/SHACL test, legal-article mapping, minimal 4-level decision logic | Automation in Construction / J. Building Engineering / Buildings |
| Paper 3 (bonus) | Field Feasibility of a Data-Informed Digital Twin Framework for Condition-Based Inspection Support at Rapexco | Field deployment, operational baseline, traceability scenarios, inspection-record workflow | JCSHM / relevant Q2–Q3 |
| Paper 4 (optional) | From Condition Evidence to Inspection Priority | Four-level decision logic, expert scenario review | May merge into Paper 3 |

# 6.  Making the QLXD core unmistakable (Paper 2 / C5)

Three things must be embedded in Paper 2 — this is where the thesis earns its discipline identity.

- CEI = first-class attribute of the chain. Evidence is linked together with its own confidence, not linked bare. This turns a static identifier chain into an evidence-weighted chain and distinguishes it from ordinary IFC linkage.

- RCQ — relationship / decision competency question. “For a given action level, can we trace back the complete evidence + CEI + component + the legal article that justifies it?” This is the question that carries the management contribution.

- Legal-mapping table. Each action level (Normal → Watch → Inspect → Priority) mapped to a specific state-management obligation by article (Luật Xây dựng 135/2025; NĐ 207/2026/NĐ-CP; TT 32/2026/TT-BXD; QĐ 46/2026/QĐ-UBND Khánh Hòa; Công văn 3839). Framed as compliance-capacity building, not mandatory-monitoring overclaim.

Note: the four states are locations (apex, BCJ, brace, healthy), not severity grades — which is exactly why traceability (“which component does this evidence belong to?”) is the natural framing and why DSI/ordinal severity is prohibited.

# 7.  Work packages

| WP | Content | Primary output |
| --- | --- | --- |
| WP1 — Lab evidence | Labelled dataset, run registry, sensor configs, run-aware/LORO, sensor-mode verification (incl. ResNet1D), CEI derivation | Reproducible lab evidence with confidence — not field diagnosis |
| WP2 — Traceability-to-decision (core) | Formal chain + CEI attribute, identifier schema, pre-registered SCQ/VCQ/RCQ, invalid-data/SHACL test, legal-article mapping, minimal 4-level logic, end-to-end lab demo | Verifiable, accountable traceability-to-decision framework |
| WP3 — Field feasibility (bonus) | Rapexco deployment (reference-informed placement), operational baseline, field scenarios, inspection-record workflow | Field-feasibility evidence — not field damage diagnosis |
| WP4 — Decision-support synthesis | Extended Normal→Watch→Inspect→Priority logic, case scenarios, facility-manager review (may fold into WP2/WP3) | Transparent, unweighted, human-reviewed decision logic |

# 8.  Validation ladder

| Level | Meaning |
| --- | --- |
| V1 — Lab validity | Controlled connection states are distinguishable and repeatable under run-aware/LORO evaluation; CEI reflects evidence confidence |
| V2 — Traceability & decision validity | Identifier chain runs bidirectionally (evidence ↔ component ↔ record ↔ action); RCQ resolves action → evidence+CEI+component+legal article; invalid data is caught |
| V3 — Field feasibility | Framework deploys at Rapexco; data return; traceability scenarios execute |
| V4 — Decision validity | Recommendations are transparent, explainable, and judged reasonable by facility management |

# 9.  Evidence gates

G1 dataset integrity & run-aware evaluation  ·  G2 traceability model, CEI attribute & competency questions  ·  G3 end-to-end lab traceability-to-decision demo (incl. invalid-data test)  ·  G4 field mapping & baseline feasibility (Rapexco)  ·  G5 inspection-action scenario review  ·  G6 Paper 2 submission  ·  G7 Paper 3 submission & thesis synthesis.

No FEM calibration, MAC, equivalent-stiffness, or FEM sensor-sensitivity gate exists. Current status: G1 materially strengthened but experimentally open (LORO + ResNet1D provenance pending); G2 strongest but needs pre-registered CQs; G3–G5 open.

# 10.  Allowed and prohibited claims

## Allowed

- Lab state evidence distinguishes controlled connection states under leakage-controlled evaluation.

- Sensor configuration influences classification more strongly than model-architecture choice.

- CEI is a confidence/evidence indicator attached to condition evidence.

- The traceability chain links evidence + CEI to components and inspection records, verified through pre-registered competency questions.

- An inspection decision can be justified and its accountability traced back to evidence, confidence, component, and legal article.

- The framework is feasibly deployable at a real building.

- The nominal FEM provides a sensor-placement reference.

## Prohibited

- Field damage diagnosis without confirming inspection; direct lab-to-field classifier transfer.

- Any claim based on a calibrated FEM; inference of bolt preload or stiffness degradation from FEM.

- Quantitative transfer of 1:10 conclusions to the real building.

- Ordinal severity / DSI; describing CEI as physical severity.

- RUL / predictive maintenance; weighted Health Index; “optimal” sensor placement; autonomous maintenance decisions; general AI-superiority.

# 11.  Role of the nominal FEM

FEM is retained solely as a nominal, uncalibrated, reference-only design model. Permitted: (i) preliminary justification of field sensor placement; (ii) illustration of component locations; (iii) qualitative mechanical hypotheses for Paper 1 anomalies (BCJ F1 collapse under S2; Apex↔BCJ confusion) in Discussion/Limitation, labelled “hypothesis, not confirmed.” Prohibited: calibration, damage diagnosis, stiffness-degradation inference, quantitative lab-to-field transfer, and appearance in the name of any RQ, WP, chapter, paper, or gate. Every mention carries the qualifier “nominal, uncalibrated, reference-only, not used for damage diagnosis.”

# 12.  Execution roadmap (3 years)

## Immediate blockers

- Verify ResNet1D sensor mode (this week). No ResNet1D number enters Paper 1 until resolved.

- Lock the re-framed RQ2 sentence (§3) — it shapes all of Paper 2.

## Year 1

- Paper 1: lock run registry, split-before-windowing, LORO (6 folds, common seeds), train-only preprocessing, run-level uncertainty. Narrative: sensor configuration dominates architecture (RF macro-F1 ~0.862 leads; 1D-CNN S12 ~0.841; ResNet1D ~0.828 corroborating only). DSI removed. → submit to Sensors.

- Paper 2 (parallel, no site needed): pre-register SCQ/VCQ/RCQ with a management lens; formalise CEI as a chain attribute; build the end-to-end lab demo incl. invalid-data test; draft the legal-mapping table.

## Year 2

- Finish and submit Paper 2 (G6). Acquire missing RQ2 full texts (3II2WKLN, NUTL57KJ, Z4IBWW9Y).

- Only after Papers 1–2 are submitted: prepare Rapexco field sensor register + BIM mapping; predefine completeness, drift, environmental-coverage, baseline and alert-to-inspection protocols (no universal baseline duration imposed).

## Year 3

- Paper 3 (bonus) if the site window holds; otherwise the thesis stands on 2×Q3. Thesis synthesis and defence (G7).

## Discipline guardrail

Do NOT add new technology layers (advanced autoencoders, Edge AI, RUL, full PBSHM, commercial DT, Smart City) while Papers 1–2 are unsubmitted. This is a recurring pattern to watch: new layers tend to appear when core deliverables are unreported. Hold scope.

# 13.  Post-PhD extensions (deferred, ordered by value-nearness)

- Generalise the CEI-weighted traceability framework to other structure/evidence types (bridges, high-rise, industrial infrastructure).

- Formalise CEI as an independent, benchmarked indicator.

- Calibrated FEM + model updating for the two Paper 1 anomalies (preserves the firewall).

- Automated referential-integrity + SHACL at multi-building scale.

- Predictive maintenance / RUL (furthest; correctly out of PhD scope).

# 14.  Terminology control

Governed by TERMINOLOGY_CONTROL_CURRENT.md (lineage v1.1), unchanged by v2. Allowed: condition evidence; state-change evidence; component-level traceability; traceability-to-decision; BIM-linked inspection record; field feasibility; inspection–maintenance support; nominal reference model; reference-informed sensor placement; confidence/evidence indicator (CEI); justification & accountability. Controlled/removed: calibrated FEM; physics-informed condition evidence; equivalent stiffness degradation; mechanical damage interpretation; optimal sensor placement; FEM-based diagnosis; damage severity/DSI; RUL; predictive maintenance; autonomous maintenance decision. Every FEM mention carries the mandatory qualifier. Run the keyword check before any gate closure.

End of Charter v2. All subsequent work — papers, evidence files, slides, agent outputs — follows this axis: RQ1 + RQ2 as the load-bearing spine, RQ2/Paper 2 as the Construction-Management identity pillar, RQ3/Rapexco as bonus.